## Slide 1
TRAK FOOTBALL
PRE-PILOT ENGINEERING REVIEW
PROJECT REVIEW · V1.0
Twenty-five things to settle before kickoff.
BRIEF
PRE-PILOT CODEBASE AUDIT
ITEMS
25 ACROSS FOUR TIERS
WINDOW
THIS WEEK → WEEK 4
DATE
MAY 2026
Notes: Welcome. This is the pre-pilot engineering review for Trak Football. I've been through the codebase end-to-end, and what I want to walk you through today is twenty-five specific things we should investigate, in priority order. The headline is encouraging: I think the pilot can launch — but only if we settle five specific items first. Everything else in this deck is about what we do after that, in week one, weeks two through four, and post-pilot. Plan for about twenty-five minutes plus questions.

## Slide 2
TRAK FOOTBALL
RECOMMENDATION · 01 / 25
VERDICT
The pilot can launch — once five blockers clear.
The architecture is sound and most of the right pieces are in place. What's missing is the safety net: secret hygiene, a real check of the security model, an error boundary, indexes, and a single source of truth on what actually shipped.
GREEN-LIGHT CONDITIONS
Five P0 items, cleared and signed off before any external user signs in.
01
Confirm and rotate any leaked Supabase key
02
Reconcile STATE.md with shipped code
03
Adversarially test RLS tenant isolation
04
Ship a global React error boundary
05
Add indexes on the three hot tables
PROJECT REVIEW · V1.0
TRAK FOOTBALL
Notes: Let me put the recommendation up front so the rest of the deck is in context. The pilot can launch, but it should not launch this week. Five P0 items have to clear first. They're listed here on the right. The pattern is consistent: these are the items where, if we get them wrong, a single pilot user can either see another user's data, brick the app for everyone, or trigger a performance regression we can't recover from at the table level. None of them are particularly hard. The work this week is mostly about confirming, not building. If we close these five, I'm confident green-lighting the pilot the following Monday.

## Slide 3
TRAK FOOTBALL
CATALOGUE · 02 / 25
SCOPE
Twenty-five investigations, four risk tiers, one decision: when to kick off.
P0 · BLOCKER
5
Resolve before any pilot user signs in
This week
P1 · HARDENING
6
Close out in launch week one
Week 1
P2 · WATCH
7
Monitor and patch during the pilot
Weeks 2 – 4
P3 · PRE-SCALE
7
Close before scaling beyond the pilot
Post-pilot
CATALOGUE OVERVIEW
02 / 25
Notes: Here's the full catalogue at a glance. Twenty-five items, sorted into four tiers. Five P0 blockers that have to land before any external user signs in. Six P1 items that we should close in launch week one — they don't block, but they become regret debt fast. Seven P2 items we monitor during the pilot itself, weeks two through four. And seven P3 items that need to close before we scale past the pilot — accessibility, CI, observability, the GDPR work, and the business model. The point of this slide is to set expectations on volume and timeline.

## Slide 4
TRAK FOOTBALL
ORIENTATION · 03 / 25
HOW TO READ THIS DECK
One item per slide for P0. Clusters by theme for P1 – P3.
P0 is the only tier where every item gets its own slide — these are the launch-blocking ones. Lower tiers are grouped so the deck stays the right length for the time we have.
EACH ITEM SHOWS
A short verdict-style title, the original investigation question, why it matters, and the proposed owner / window.
TIER BADGE
Colored chip in the top-left of every item slide — P0, P1, P2 or P3 — so you always know the urgency you're looking at.
NUMBERING
Item numbers match the source catalogue (#1 – #25). Use them in follow-up tickets so nothing slips between systems.
CLOSING
The last three slides collapse everything into a domain heatmap, this-week sequencing, and the conditions for green-lighting the pilot.
HOW TO READ THIS DECK
03 / 25
Notes: A quick orientation on how to read the rest of the deck. The P0 items each get their own slide, because every one of them is launch-blocking and I want time on each. The lower tiers are clustered by theme — so two slides for P1, two for P2, two for P3. Each item slide has the same structure: a verdict-style title, the original investigation question, why it matters, and a proposed owner and effort estimate. Item numbers match the source catalogue so you can use them in tickets after this meeting.

## Slide 5
TRAK FOOTBALL
P0 · SECTION OPENER
TIER P0 · PRE-PILOT BLOCKERS
Five things must clear before any pilot user signs in.
If one of these is still open on launch day, delay launch. These are not "would be nice" — they are the items that could expose user data, brick the app, or quietly degrade it to unusable inside the first week.
ITEMS 1 – 5
5
THIS WEEK
Notes: Now to P0. Five items. The framing for this section is simple: if any one of these is still open on launch day, we delay launch. Three of the five live in security or implementation fidelity — they're about confirming the foundation is what we think it is. The other two are operational gaps: an error boundary and database indexes. None of them are speculative; all five are concrete things to do this week.

## Slide 6
TRAK FOOTBALL
P0 · ITEM 1 OF 25 · SECURITY
P0
BLOCKER
ITEM 01
SECURITY
Confirm the Supabase key has not entered git history — and rotate it if it has.
Run git log --all --full-history -- .env . A single historical commit makes the anon key permanently public on any clone or fork, no matter how many later commits scrub it.
OWNER
Backend lead
EFFORT
~ 2 hours
DUE
Before any deploy
HOW WE'LL RESOLVE IT
Audit history of
.env
,
.env.local
, and any committed config across
all
branches and tags.
If a key ever landed: rotate the anon and service keys in Supabase, redeploy.
Add
.env*
to
.gitignore
if absent; install a pre-commit secret scanner (gitleaks).
Document the rotation procedure so we can repeat it without ceremony.
Why now: rotating a key after a pilot user has signed in is a recovery exercise. Doing it now is a five-line config change.
P0 · ITEM 1 — SECRETS IN GIT HISTORY
04 / 25
Notes: P0 item one. The Supabase anon key — has it ever been committed to the repository? The command to check is on the slide. The reason this is urgent: a key that has ever been in git history is permanently public to anyone who has cloned, forked, or even shallow-pulled the repo at any point, regardless of whether we later scrubbed it. If it ever leaked, we rotate today. The good news is that the audit takes about two hours and the rotation is a redeploy. We also want to wire in a pre-commit secret scanner so we don't have to think about this again. The owner is the backend lead.

## Slide 7
TRAK FOOTBALL
P0 · ITEM 2 OF 25 · IMPLEMENTATION FIDELITY
P0
BLOCKER
ITEM 02
IMPLEMENTATION FIDELITY
Reconcile STATE.md against shipped code before trusting either.
STATE.md lists all 31 tasks as "pending"; the most recent commit message says "all 6 milestones implemented." Until we know which is right, we cannot scope the pilot — and we cannot estimate the remaining work.
OWNER
Tech lead + PM
EFFORT
½ day pair
DUE
This week
HOW WE'LL RESOLVE IT
Pair walk the 31 task list against the running app, tagging each as
done · partial · broken · not started
.
Re-write STATE.md so it reflects reality — once. Then keep it current per merge.
Promote any "partial" task back into the backlog with explicit acceptance criteria.
Flag anything that's drifted into "implemented but not specified" — those are tomorrow's bugs.
Why now: you can't run a pilot on code you believe is complete. The cost of finding out mid-pilot is a stakeholder conversation we don't want to have.
P0 · ITEM 2 — STATE.MD VS ACTUAL CODE
05 / 25
Notes: P0 item two. We have a conflict between STATE.md, which lists thirty-one tasks as pending, and the most recent commit message, which claims all six milestones are implemented. Until we know which is right, we don't actually know what we're shipping into the pilot. The fix is a half-day pair walk-through — tech lead and PM, sitting together, running the app and ticking each task as done, partial, broken, or not started. Then STATE.md becomes the source of truth, and we keep it current per merge. You cannot run a pilot on code you believe is complete; that's the line that matters here.

## Slide 8
TRAK FOOTBALL
P0 · ITEM 3 OF 25 · SECURITY
P0
BLOCKER
ITEM 03
SECURITY · MULTI-TENANT
Break tenant isolation in the browser before a pilot user does.
RLS policies exist on paper but have never been adversarially tested. Sign in as Player A, open the browser console, and try to read Player B's matches with the Supabase client directly. If anything comes back, the policy is wrong.
OWNER
Security reviewer
EFFORT
~ 3 hours
DUE
This week
HOW WE'LL RESOLVE IT
Seed two players, two coaches, two clubs into a staging project.
Run the manual cross-tenant probe in the browser for
every
table: matches, assessments, squad_players, profiles, invites.
For every leak, tighten the policy and re-run. Codify each probe as a test fixture.
Keep a "tenant isolation" checklist alongside every future schema change.
Why now: RLS is the only thing standing between Player A and Player B's data. We've never confirmed it actually does.
P0 · ITEM 3 — RLS ISOLATION
06 / 25
Notes: P0 item three. Multi-tenant isolation. We have RLS policies in place on every table, but we have never adversarially tested them. The probe is straightforward: sign in as Player A in one browser, open the Supabase client in the console, and try to read Player B's matches, assessments, profile, anything. If any row comes back, the policy is wrong. We do this for every table, fix what we find, and then codify each probe as a test fixture so we never regress. About three hours, owned by whoever's playing the security reviewer role this week.

## Slide 9
TRAK FOOTBALL
P0 · ITEM 4 OF 25 · ERROR HANDLING
P0
BLOCKER
ITEM 04
ERROR HANDLING
Wrap the app in an error boundary before a single bad input lands.
There is no React error boundary anywhere in the tree. The first unhandled exception from a pilot user blanks the entire screen — and we will hear about it from them, not from logs.
OWNER
Frontend lead
EFFORT
~ 4 hours
DUE
This week
HOW WE'LL RESOLVE IT
Add a global error boundary at the router root with a graceful "something broke, here's how to get back" screen.
Add per-route boundaries for the three role homes so one screen's crash doesn't take the app with it.
Wire boundary errors into the logging sink (see P3 item 21) the moment that exists.
Trigger a synthetic error in dev to confirm the fallback actually renders.
Why now: one corrupt match record from a pilot user shouldn't end their session — or our trial.
P0 · ITEM 4 — ERROR BOUNDARY
07 / 25
Notes: P0 item four. There is no React error boundary anywhere in the app. The first time a pilot user triggers an unhandled exception — a corrupt match record, a date in the wrong format, a missing field — they get a blank white screen. And we will hear about it from them, not from logs. The fix is half a day: a global boundary at the router root with a graceful fallback, and per-route boundaries for the three role homes so one screen's crash doesn't take the app down with it. Frontend lead owns this. When the logging sink lands later in P3, we wire boundary errors into it.

## Slide 10
TRAK FOOTBALL
P0 · ITEM 5 OF 25 · DATABASE
P0
BLOCKER
ITEM 05
DATABASE · PERFORMANCE
Add indexes before thirty users hit a full table scan.
Open Supabase Studio and inspect indexes on matches, coach_assessments, and squad_players . Expectation: none exist beyond primary keys. Every list view is currently a full table scan.
OWNER
Backend lead
EFFORT
½ day with migrations
DUE
This week
HOW WE'LL RESOLVE IT
Add a foreign-key index on
matches.player_id
and
matches.created_at
for history queries.
Index
coach_assessments.player_id
+ composite on
(coach_id, created_at)
.
Index
squad_players.squad_id
and
squad_players.player_id
— both sides of the lookup.
Re-run the worst three queries with EXPLAIN; confirm we're hitting indexes, not seq scans.
Why now: indexes are cheap before there's data. They become a planned-migration conversation later.
P0 · ITEM 5 — DATABASE INDEXES
08 / 25
Notes: P0 item five. Database indexes. Open Supabase Studio, look at the matches, coach_assessments, and squad_players tables, and confirm what I expect to be true: no indexes beyond the primary keys. Every list query is currently a full table scan. With thirty pilot users this is fine on day one and noticeably slow by week three. The fix is a half-day of migrations — foreign-key indexes on the obvious columns, plus a composite or two for the most common access patterns — and then re-running the worst three queries with EXPLAIN to confirm we're hitting indexes. Indexes are cheap to add before there's data and expensive once there is.

## Slide 11
TRAK FOOTBALL
P0 · RECAP · 09 / 25
P0 · RECAP
Five items, four owners, one week to settle them all.
#
INVESTIGATION
DOMAIN
OWNER
EFFORT
STATUS
01
Audit git history for leaked Supabase keys
Security
Backend lead
~ 2h
Open
02
Reconcile STATE.md against shipped code
Fidelity
Tech lead + PM
½ day
Open
03
Adversarially test RLS tenant isolation
Security
Security reviewer
~ 3h
Open
04
Ship a global React error boundary
Error handling
Frontend lead
~ 4h
Open
05
Add indexes on the three hot tables
Database
Backend lead
½ day
Open
P0 — RECAP AND OWNERS
09 / 25
Notes: Recap of P0. Five items, four owners — the backend lead carries two, and PM partners with the tech lead on the STATE.md reconciliation. The total effort is comfortably under a person-week. The status column starts as 'open' across the board. By Friday, every row should read 'done', and we'd run a fifteen-minute review to confirm before green-lighting the following Monday's pilot kickoff.

## Slide 12
TRAK FOOTBALL
P1 · SECTION OPENER
TIER P1 · HARDENING
Six items that should close before the end of launch week.
P1 is what turns a working app into a production app: tests, types, error surfacing, session handling, and a basic password floor. None block launch — all become regret debt within a fortnight if we don't get to them.
ITEMS 6 – 11
6
WEEK 1
Notes: Moving to P1. Six items, all hardening work that should close inside launch week one. These don't block launch — the app works without them — but they all become regret debt within a fortnight. I've split the six into two themed slides: cluster A is testing and types, cluster B is runtime safety. The headline for the section: P1 is the work that turns a working app into a production app.

## Slide 13
TRAK FOOTBALL
P1 · ITEMS 6, 7, 11 OF 25 · TESTING & CODE QUALITY
P1 · CLUSTER A
P1
HARDENING
Stand up the test loop, the type loop, and the strict-mode build the project already paid for.
Item 06
· TESTING
Stand up the end-to-end test we already paid for.
Playwright is installed and configured but zero test files exist. The core player loop — sign up → log match → see band — has never been exercised end-to-end by anything other than a human.
ACTION: 3 SMOKE TESTS COVERING EACH ROLE'S HAPPY PATH.
Item 07
· CODE QUALITY
Turn TypeScript strict mode on and pay the bill once.
noImplicitAny, strictNullChecks, and unused-variable checks are all disabled. Flipping them on surfaces the type debt today, while it's still small enough to fix.
ACTION: ENABLE STRICT IN TSCONFIG.APP.JSON ; TRIAGE ERRORS.
Item 11
· CODE QUALITY
Ship a build that compiles clean under strict.
A build that only works with strict settings off is not production-grade. Once 07 is done, 11 is the ratchet that keeps it done — fail the pipeline on any new loose type.
ACTION: NPM RUN BUILD IN STRICT; GATE MERGES ON IT.
P1 · CLUSTER A — TESTING & TYPES
10 / 25
Notes: P1 cluster A. Three items, all about confidence in what we ship. Item six: Playwright is already installed and configured. Zero test files exist. The smallest meaningful step is three end-to-end smoke tests, one per role's happy path, and we'd have them in a day. Item seven: TypeScript strict mode is off — no implicit any, no strict null checks, no unused variable checks. Turning it on surfaces the type debt today, while it's small. Item eleven is the ratchet: once seven is done, gate merges on a clean strict build so we can't slip backwards.

## Slide 14
TRAK FOOTBALL
P1 · ITEMS 8, 9, 10 OF 25 · RUNTIME SAFETY
P1 · CLUSTER B
P1
HARDENING
Make every failure visible to the user — and every weak password impossible.
Item 08
· ERROR HANDLING
Surface every Supabase write failure to the user.
Audit every .insert() and .update() call. Silent failures mean a coach assesses a player, the request fails, the UI says nothing, and the assessment is gone. We learn about it from the coach.
ACTION: LINT RULE + MANUAL SWEEP; TOAST ON EVERY ERROR PATH.
Item 09
· ERROR HANDLING
Handle the session that just expired .
autoRefreshToken is on, but no explicit expiry handler exists. Clear the token mid-session and the app hangs instead of redirecting cleanly to sign-in. Pilot users will hit this on the second day.
ACTION: GLOBAL AUTH-STATE LISTENER; REDIRECT ON SESSION LOSS.
Item 10
· SECURITY
Raise the password floor to eight characters .
Both Supabase and the frontend currently accept 6-character passwords. With minors in scope, the minimum is 8 and the message at signup should say so before the request goes out.
ACTION: SUPABASE AUTH SETTING + FRONTEND VALIDATOR + COPY.
P1 · CLUSTER B — RUNTIME SAFETY
11 / 25
Notes: P1 cluster B. Three items about making the runtime honest. Item eight: every Supabase insert and update needs to check the error return and surface it to the user. The failure mode today is silent — coach assesses a player, request fails, UI says nothing, assessment is gone. We learn about it from the coach. Item nine: sessions expire, autoRefreshToken doesn't catch every case, and the app currently hangs instead of redirecting to sign-in. Add a global auth-state listener. Item ten: the password floor is six characters in both Supabase and the frontend. With minors in scope, it's eight. Two-line fix.

## Slide 15
TRAK FOOTBALL
P2 · SECTION OPENER
TIER P2 · WATCH DURING THE PILOT
Seven items to monitor while the pilot is live.
P2 items are unlikely to break on day one but will accumulate quietly across the four weeks of the pilot. Pagination, data immutability, edge cases, and stale local state — each one becomes visible when something else goes wrong.
ITEMS 12 – 18
7
WEEKS 2 – 4
Notes: On to P2. Seven items to watch during the pilot weeks. The framing here is different from P0 and P1. These items are unlikely to fail on day one. They're the slow leaks — things that get worse as data accumulates, or that fail only on edge cases. So instead of 'fix before launch', the disposition is 'monitor weekly during the pilot, patch as needed'. Two themed slides: data integrity, then scale and UX.

## Slide 16
TRAK FOOTBALL
P2 · ITEMS 14, 15, 16 OF 25 · DATA INTEGRITY
P2 · CLUSTER A
P2
WATCH
Treat assessment history as a permanent record — and prove the maths at the edges.
Item 14
· SECURITY
Lock down FOR ALL RLS policies.
FOR ALL implicitly grants DELETE. A coach could erase their own assessment history; a player could delete a coach's record of them. Historical records should be immutable — split the policies by verb.
ACTION: REVIEW EACH POLICY; REPLACE ALL WITH SELECT/INSERT/UPDATE.
Item 15
· DATABASE
Stress the band calculation at its extremes.
Six sliders feed into the assessment band, and the boundary behaviour has never been tested. Submit with all-zeros, all-tens, and mixed-edge values — confirm the band that comes out is the one a human would expect.
ACTION: 6 BOUNDARY FIXTURES, LOCKED IN AS UNIT TESTS.
Item 16
· DATABASE
Constrain invite codes before two coaches collide.
No unique constraint is visible on TRK-XXXX invite codes. Two coaches sharing one code routes their players to whichever account got there first. Quiet, hard to debug, easy to prevent.
ACTION: ADD UNIQUE CONSTRAINT; RETRY-ON-COLLISION IN GENERATOR.
P2 · CLUSTER A — DATA INTEGRITY
13 / 25
Notes: P2 cluster A. Three items about treating data correctly. Item fourteen: our RLS policies use FOR ALL, which implicitly grants DELETE. A coach could erase their own assessment history; a player could delete a coach's record of them. Historical records should be immutable. We split the policies by verb. Item fifteen: the assessment band calculation takes six slider values. We've never tested it at boundary values — all zeros, all tens, mixed edges. Six fixtures, locked in as unit tests. Item sixteen: TRK invite codes have no unique constraint that I can see. Two coaches with the same code means players route to whichever account got there first. Quiet, hard to debug.

## Slide 17
TRAK FOOTBALL
P2 · ITEMS 12, 13, 17, 18 OF 25 · SCALE & UX
P2 · CLUSTER B
P2
WATCH
Performance, bundle, stale state, leaderboard privacy — the slow leaks.
Item 12
Paginate match history before it gets long.
No .range() call is visible in useMatches . With 30+ matches per pilot player, the history screen pulls everything every time. Add a cursor and a "load more" before someone tracks a full season.
PERFORMANCE
Item 13
Measure the initial JS payload.
24 Radix components, Recharts, multiple icon sets. Run npm run build, inspect dist/ . Mobile pilot users on slow connections will feel anything over ~250KB of first-paint JS.
PERFORMANCE
Item 17
Expire stale onboarding state.
PENDING_PROFILE_KEY has no expiry timestamp. If a user abandons onboarding and returns days later, they restart from a phantom mid-state. Stamp it with a TTL, or clear on every successful sign-in.
CODE QUALITY
Item 18
Audit leaderboard privacy at aggregate level.
A position leaderboard queries across players. We need to verify that aggregate views never let a player infer which coach owns them, or which club another player belongs to. Test before adding the feature, not after.
SECURITY
P2 · CLUSTER B — SCALE & UX
14 / 25
Notes: P2 cluster B. Four items about how the app behaves at scale and under stale state. Item twelve: no .range() in useMatches, so the history screen pulls everything every time. Add a cursor before someone tracks a full season. Item thirteen: measure the initial JS payload — twenty-four Radix components plus Recharts plus multiple icon sets will be felt on mobile. Item seventeen: PENDING_PROFILE_KEY in localStorage has no TTL, so abandoned onboarding state lives forever. Item eighteen: when we add the leaderboard, audit that aggregate queries don't let a player infer their coach or another player's club. Test before adding the feature, not after.

## Slide 18
TRAK FOOTBALL
P3 · SECTION OPENER
TIER P3 · PRE-SCALE
Seven items to close before scaling beyond the pilot.
P3 covers the work that converts a successful pilot into a product: accessibility, CI/CD, observability, GDPR, Storybook hygiene, bundle discipline, and the monetization model. Each becomes urgent the moment we sign a second customer.
ITEMS 19 – 25
7
POST-PILOT
Notes: P3. Seven items to close before scaling beyond the pilot. The framing: each of these becomes urgent the moment we sign a second customer. They're not urgent today because we have one customer and thirty users. They will be urgent in three months. Two themed slides: quality and operations, then compliance and strategy.

## Slide 19
TRAK FOOTBALL
P3 · ITEMS 19, 20, 21, 23 OF 25 · QUALITY & OPERATIONS
P3 · CLUSTER A
P3
PRE-SCALE
Make the app accessible, the deploys repeatable, the logs real, the stories honest.
Item 19
Restore accessibility the viewport meta tag broke.
user-scalable=no in index.html directly violates WCAG 1.4.4. Run axe-core across all three role homes and triage the rest. Accessibility for minors is not optional.
ACCESSIBILITY
Item 20
Replace manual deploys with a real pipeline.
No .github/workflows/ exists. Every deploy is a person clicking through Lovable. That's a single point of failure and an audit problem the moment a second engineer joins the project.
OPERATIONS
Item 21
Wire up logging — three calls is not observability.
Three console.error calls across 132 files is effectively zero visibility. Pick Sentry (or equivalent), wire it into the error boundary from item 04, and start every incident with data instead of a guess.
OPERATIONS
Item 23
Refresh Storybook or retire it.
Storybook v10 is installed; the stories were written against early scaffolding and have drifted. Either bring them current to the shipped components or remove the dependency. Stale stories are worse than no stories.
TESTING
P3 · CLUSTER A — QUALITY & OPERATIONS
16 / 25
Notes: P3 cluster A. Four items about operational maturity. Item nineteen: user-scalable=no in the viewport meta tag is a direct WCAG 1.4.4 violation. Run axe-core across the role homes and triage the rest. Accessibility for minors is not optional. Item twenty: there's no GitHub Actions workflow, so every deploy is a person clicking through Lovable. Single point of failure. Item twenty-one: three console.error calls across 132 files is effectively no observability. Pick Sentry, wire it into the error boundary from item four. Item twenty-three: Storybook is installed, stories were written against early scaffolding, they've drifted. Refresh or retire — stale stories are worse than no stories.

## Slide 20
TRAK FOOTBALL
P3 · ITEMS 22, 24, 25 OF 25 · COMPLIANCE & STRATEGY
P3 · CLUSTER B
P3
PRE-SCALE
Build the deletion path the minors regulation demands, trim the bundle, name the business model.
Item 22
· COMPLIANCE
Build the data-deletion path for minors.
The pilot involves minors. Parental consent and deletion rights are legal obligations, not nice-to-haves. We need a self-serve account deletion flow and a privacy policy linked from the app — both before pilot close.
ACTION: DELETION ENDPOINT + LINKED PRIVACY POLICY.
Item 24
· PERFORMANCE
Tree-shake Recharts and audit icon imports.
A wildcard Recharts import adds ~200KB un-tree-shaken. Combined with multiple icon sets we already ship, the bundle is heavier than it needs to be. One afternoon of import discipline saves a perceptible amount on mobile.
ACTION: SWITCH TO NAMED IMPORTS; MEASURE DELTA IN DIST/.
Item 25
· BUSINESS
Pick a monetization model before the pilot ends.
No monetization is documented anywhere in the project. The coach is identified as the acquisition channel — but no pricing, conversion point, or paid tier is named. We need a working hypothesis before the pilot's last week, so the next conversation with users includes "how much".
ACTION: WRITTEN PRICING HYPOTHESIS + CONVERSION MOMENT.
P3 · CLUSTER B — COMPLIANCE & STRATEGY
17 / 25
Notes: P3 cluster B. Three items that are not purely engineering. Item twenty-two: parental consent and account deletion are legal obligations for minors, full stop. We need a self-serve deletion path and a linked privacy policy. This one needs an owner outside engineering. Item twenty-four: tree-shake Recharts and audit our icon imports — wildcard imports likely add about two hundred kilobytes the bundle doesn't need. Item twenty-five: there is no documented monetization model anywhere in the project. The coach is identified as the acquisition channel, but no pricing, no conversion point, no paid tier is named. We need a working hypothesis before the pilot's last week so we can have the 'how much' conversation while the users are still engaged.

## Slide 21
TRAK FOOTBALL
WHERE THE RISK CONCENTRATES · 18 / 25
DOMAIN HEATMAP
Security and database concentrate the urgency. Ops and accessibility wait.
DOMAIN
P0
P1
P2
P3
TOTAL
Security
01
03
10
14
22
5
Database
05
—
12
15
16
—
4
Error handling
04
08
09
—
—
3
Code quality
—
07
11
17
18
—
4
Performance
—
—
12
13
24
3
Fidelity / testing
02
06
—
23
3
Operations
—
—
—
20
21
2
Accessibility & business
—
—
—
19
25
2
WHAT THIS TELLS US
Security and database items dominate the urgent tiers. Three of five P0 items live there — which means the people most likely to be busy this week are the backend lead and a security reviewer.
Operations and accessibility wait — but not forever. Both are entirely in P3. The cost of leaving them open is small during a 30-user pilot, large at the second customer.
The business model is the only strategy item. Item 25 is the one entry that won't be solved in the IDE.
HEATMAP BY DOMAIN
18 / 25
Notes: Here's where the work concentrates. Security carries five items across all four tiers — three urgent ones, which means the security reviewer and the backend lead are going to be the busiest people this week. Database is next with four, three of which are P2. Error handling, code quality, and fidelity each have three. Operations and accessibility wait entirely in P3 — fine for a pilot, urgent at customer two. The single business item is twenty-five, and it's the only entry that won't be answered in the IDE. The legend on the right summarizes what this distribution means for staffing.

## Slide 22
TRAK FOOTBALL
SEQUENCE · 19 / 25
THIS WEEK · SUGGESTED ORDER
Run the five P0 items in this order. Each unblocks the next.
1
MON
Audit git history.
Cheapest, fastest, and the only one that has to land before any deploy. If keys leaked, today is the day to rotate.
2
MON – TUE
Reconcile STATE.md.
Gives the rest of the week an honest picture of what's actually done. Without it, every other item is guesswork.
3
TUE – WED
Probe RLS isolation.
Manual cross-tenant test in the browser. Surface every leak; tighten policy; codify as a test fixture.
4
WED – THU
Ship the error boundary .
Global + per-route. Synthetic error in dev to confirm the fallback renders before merging.
5
THU – FRI
Add indexes.
Migrations on the three hot tables. EXPLAIN-verify the worst queries before close-of-week.
OUTCOME BY FRIDAY
All five P0 items closed, owners signed off, evidence captured in the project tracker.
FRIDAY REVIEW
15-minute standup: confirm each item is done, decide whether to green-light the following Monday's pilot kickoff.
THIS-WEEK SEQUENCE
19 / 25
Notes: Concretely for this week, here's the order I'd run the five P0 items in. Monday: the git history audit. It's the cheapest, the fastest, and the only one that has to land before any deploy. If keys leaked, we want to know on Monday. Monday into Tuesday: reconcile STATE.md, because the rest of the week is informed by that picture. Tuesday into Wednesday: the RLS probe. Wednesday into Thursday: ship the error boundary. Thursday into Friday: indexes. By Friday close, all five should be done, with evidence in the tracker. A fifteen-minute Friday review to confirm and to green-light Monday.

## Slide 23
TRAK FOOTBALL
DECISION · 20 / 25
GREEN-LIGHT CONDITIONS
Pilot launches when all five boxes are checked.
Not before. Not partially. The boxes are deliberately small in number — each is binary, each has a named owner, and each is verifiable from outside the engineering team.
Supabase keys verified clean (or rotated)
BACKEND LEAD
STATE.md reflects the running app
TECH LEAD + PM
RLS isolation passes the browser probe
SECURITY REVIEWER
Error boundary live in prod
FRONTEND LEAD
Indexes deployed on three hot tables
BACKEND LEAD
GREEN-LIGHT CONDITIONS
20 / 25
Notes: Green-light conditions for the pilot, all in one place. Five boxes. They're deliberately binary — checked or not, no halfway. Each has a named owner. Each is verifiable from outside the engineering team, which matters because the green-light decision is not just an engineering call. If on Friday any of these is unchecked, we don't launch on Monday. We don't ship 'mostly ready'. The conditions are small enough in number that 'mostly' isn't a real category.

## Slide 24
TRAK FOOTBALL
OPEN QUESTIONS · 21 / 25
FOR THE TEAM TO ANSWER
Six open questions we cannot close from the codebase alone.
Q1
Who is the
single owner
of the pilot launch decision?
Each P0 item has a doer; only one person should hold the go / no-go.
Q2
How many
real users
are we inviting in pilot week one?
Index strategy and pagination thresholds depend on the actual cohort size.
Q3
What is the
incident path
when a pilot user reports a crash on a Saturday?
Without observability or on-call coverage, this is a quiet single point of failure.
Q4
Who owns
parental consent
for the minors in scope — product, ops, or legal?
Item 22 needs a named owner before pilot day one, not after.
Q5
What is our
working hypothesis
on pricing — and when do we test it?
Item 25 is the only entry we cannot answer from the IDE.
Q6
If two P0 items slip, do we
delay the pilot
or shrink the cohort?
Decide the rule now, while it's hypothetical and unemotional.
OPEN QUESTIONS FOR THE TEAM
21 / 25
Notes: Six open questions we cannot answer from the codebase. Who owns the launch decision singularly — because right now I see five doers but no single decision-maker. How many real users are in pilot week one — that sizing matters for indexes and pagination. What's the incident path on a Saturday — we don't have on-call coverage yet. Who owns parental consent — product, ops, or legal. What's our pricing hypothesis and when do we test it. And critically: if two P0 items slip on Friday, do we delay or shrink — better to decide the rule now, while it's hypothetical, than under pressure on Friday afternoon.

## Slide 25
TRAK FOOTBALL
DISCUSSION
DISCUSSION
Five blockers. One week. Then we play.
Thank you. Questions, dissent, and revised owner names all welcome — better here than on the pitch.
TRAK FOOTBALL · PRE-PILOT REVIEW
25 / 25
Notes: That's the review. Five blockers, one week, and then we play. I'm happy to take questions in any order — the items, the priorities, the owners, the timeline, or the open questions. Push back on anything that doesn't match the picture you have from the inside. Thank you.